## FFG
Item | Plans | Sub plans | Sprint 3 | [13 empty] | Sprint4
|  |  | 20170411 | 20170412 | 20170413 | 20170414 | 20170415 | 20170416 | 20170417 | 20170418 | 20170419 | 20170420 | 20170421 | 20170422 | 20170423 | 20170424 | 20170425 | 20170426 | 20170427 | 20170428 | 20170429 | 20170430 | 20170501 | 20170502 | 20170503 | 20170504
Sprint3 | add&delete mapping API integration |  | 4 | OK
| Hide function | Hide left side | 4 | 4 | OK
|  | Hide right side | 4 | 4 | 3 | OK
| Restore function | Restore left side | 4 | 4 | OK
|  | Restore right side | 4 | 4 | 4 | OK
| Save userdefined function |  | 4 | 1 | OK
| Submit snapshot to Sundeep |  |  |  | OK
| Pop up step three | [9 empty] | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  |  | 8 | 8
| common pop up add | [9 empty] | 3 | OK
| defects | pop up close -> cancel mapping |  | 2 | OK
|  | do mapping-> cosole error occurs |  | 2 | OK
|  | restore left side refresh issue |  |  |  | OK
|  | collapration modle issue | [8 empty] | OK
|  | Check with Emon for the 2 tabs issue | [8 empty] | 2 | OK
|  | Delete cookie issue search | [8 empty] | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  |  | 8 | 8
|  | User can only edit one item at one time | [13 empty] | 4 | OK
|  | Real time hide&mapping confilict | [9 empty] | 8 | 8 |  |  | 8 | OK
|  | only admin can go mapping page | [7 empty] | OK
|  | currency pop up title and disable |  |  |  | OK
Sprint4 | Gear - Load Data File (Project Admin) | [15 empty] | OK
| UI - Return link | [15 empty] | OK
| Pop up step two api integration | [23 empty] | 4
| UI - Piwik | [15 empty] | 18 | 18 | 18 | 6 |  |  |  | 6 | 6

## BIV
Item | Plans | Sub plans | Sprint 3
|  |  | 20170411 | 20170412 | 20170413 | 20170414 | 20170415 | 20170416 | 20170417 | 20170418 | 20170419 | 20170420 | 20170421 | 20170422 | 20170423 | 20170424 | 20170425 | 20170426
BIV | Install Eclipse |  |  |  |  | 1 |  |  | OK
| Install Maven |  |  |  |  | 1 |  |  | OK
| Install Tomcat |  |  |  |  | 1 |  |  | OK
| Piwik add in piwik web | [7 empty] | 12 | OK
|  | Piwik for UAT and QA | [14 empty] | 4 | OK
| Add user | UI change | [9 empty] | 12 | OK
| Defects | Add email no received email issue